LAP		 JPA		 SFGA

| Full FPN: | 453213-1-34-01 |  | FY: | 24 |  | FAN: | N/A |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Project Name: | NEIGHBORHOOD LAKES SCENIC TRAIL & TRAILHEAD IMPROVEMENTS |
| --- | --- |

| Local Agency: | Lake County | Agency Contact: (Project Manager) |  |  | GALLUS C. QUIGLEY JR. |
| --- | --- | --- | --- | --- | --- |
| Position Title: | Recreation Coordinator-Trails |  | Address: | 2401 Woodlea Road |  |
|  |  |  |  | Tavares, FL 32778 |  |
| Phone: | 352-742--3866 |  | Email: | gallus.quigley@lakecountyfl.gov |  |

PROJECT SCOPE / DESCRIPTION, TERMINI, PROJECT LENGTH:

The Neighborhood Lakes Scenic Trail & Trailhead Improvements project is with Lake County. The project consists of site development and the re-design of some facilities. The site development project has an estimated total area of 6.37+/- acres. The proposed design improvements will have site development for all the components of the project. These items will include a 20,000 square foot main building including connection to the existing water and electrical services, and to the proposed septic system. Building design is not part of scope, only footprint and utility service/connections. (2) Pavilions (20' x 30'), a playground, dog park, trails and wide-walk way paths, water fountains, picnic tables, trash cans, bike racks, and ADA accessible path system to serve the Wekiva and Neighborhood Lakes Scenic Trails at the Neighborhood Lakes Trailhead. The design services shall include survey, subsurface utility exploration, and geotechnical work. Permitting and utility coordination are anticipated. Right of way acquisition is not/ anticipated. The Agency (Recipient) shall design the project within the limits of the right of way or easements. Proposed construction improvements will include the installation of a playground, a shade structure for the playground, (2) picnic pavilions, and the installation of an 8-foot sidewalk. Other construction improvements will include the installation of a water fountain, picnic tables, benches, bike racks, and trash cans that are bear proof(single and double bins). Other construction elements may include mobilization, maintenance of traffic, erosion control, clearing and grubbing, regular and subsoil excavation, embankment (to include surcharge), and sod. All pedestrian facilities and amenities shall adhere to current America with Disabilities Act (ADA) standards. The design services shall include survey, subsurface utility exploration, and geotechnical work. Permitting and utility coordination are anticipated. Right of way acquisition is not anticipated. Lake County (Recipient) shall design the project within the limits of the right of way or easements.

CEI Procurement Method:

| In-House | Locally Funded | Advertisement | Local Agency CSC |
| --- | --- | --- | --- |

***IMPORTANT: FDOT PM - Please confirm that WP covers funding listed below before submitting for drafting***

| TOTAL PROJECT ESTIMATE: | $312,000 | (Attach engineer’s estimate) |
| --- | --- | --- |
| State Funding: | $400,000 |  |
| Local Funding: | $100,000 | Please include amounts below: Funding Shortfall ($___________) Ineligible Costs ($______________) Local Match ($100,000___________) |

ESTIMATED PROJECT SCHEDULE (MM/DD/YYYY) [**Dates in () are from previous schedule]:

| Date & Time Agreement Needed | : | 04-24-2024 |
| --- | --- | --- |
| Board Date | : | 10-28-2025 (01-21-2025) |
| Begin Design or NTP to Consultant Firm | : | 11-10-2025 (02-03-2025) |
| 30% Plans Submittal | : | 12-4-2025 (02-28-2025) |
| 60% Plans Submittal | : | 1-2-2026 (03-31-2025) |
| 90% Plans Submittal | : | 3-2-2026 (05-31-2025) |
| Final Plans Submittal | : | 4-3-2026 (06-30-2025) |
| Advertise for Construction Services | : | 5-4-2026 (07-31-2025) |
| Bid Opening Date | : | 6-5-2026 (09-01-2025) |
| Award Date | : | 7-6-2026 (09-30-2025) |
| Executed Contract Date | : | 8-7-2026 (10-31-2025) |
| Pre-Construction Date | : | 9-7-2026 (12-08-2025) |
| NTP to Contractor | : | 9-21-2026 (01-01-2026) |
| Construction Duration | : | 150 Calendar Days |
| Substantial Completion Date | : | 2-17-2027 (05-30-2026) |
| Final Acceptance Date | : | 3-17-2027 (06-30-2026) |

FDOT Use Only:

Off System		 Off System w/ On System Impacts		 On NHS		 On SHS

MAINTENANCE: On System and Off System w/ On System Impacts only

Who is responsible for maintenance of any improvements on the Department’s R/W after construction is complete?

LOCAL AGENCY                   FDOT		   OTHER: Input Entity Name

Additional Exhibits (If Required):

Landscape Maintenance (LAP Only)		 Roadway Lighting Maintenance		 Traffic Signal Maintenance

Exhibit “I” – Federal Requirements (State-Funded Only)

Terms and Conditions of Construction in Department Right-of-Way

PM Partner Review Completed By:						     Date: